## Project Plan
Task Name | Responsibility | Start | End | Days | Status
Sprint1 |  | 2018-03-14 | 2018-03-18 | 4 | Inprogress
Feature1 | Poovanesh | 2018-03-14 | 2018-03-18 | 4 | Inprogress
Feature2 | Pradeep | 2018-03-14 | 2018-03-18 | 4 | Inprogress
Feature3 | Santhosh | 2018-03-14 | 2018-03-18 | 4 | Inprogress
Sprint2
Feature4
Feature5
Feature6

## Release Plan
Sprint | Story | Start | End | Duration | Status | Release Date | Goal
1 | S001 | 2018-03-14 | 2018-03-18 | 4 | Planned | 2018-03-18 | To get the flow of the site
1 | S002 | 2018-03-14 | 2018-03-18 | 4 | Planned | 2018-03-18 | To get the tables and columns
1 | S003 | 2018-03-14 | 2018-03-18 | 4 | Planned | 2018-03-18 | To get the coding standard for the project
1 | S004 | 2018-03-14 | 2018-03-18 | 4 | Planned | - | Ongoing

## Sprint Backlog with Burndown
Backlog Item | Story Point | Responsibility | Status | Original Estimate | Day1 | Day2 | Day3 | Day4 | Day5 | Day6 | Day7 | Day8 | Day9 | Day10 | Sprint Review
S001 - Create Flow Chart | 8 | Poovanesh | Inprogress
T001 - Create Flow chart to specify the logical flow of the screens/pages
T002 - Publish the document in Github
T003 - Review the Document
T004 - Provide the registation form to pradeep
S002 - Create ERD | 8 | Pradeep | Inprogress
T001 - Create ER diagram to specify the tables and the columns that will be used through out the website
T002 - Publish the document in Github
T003 - Review the Document
S003 - Create coding standard Document | 5 | Santhosh | Inprogress
T001- Create docment to specify coding standards for creating classes, variables, packages, artifacts |  |  |  | 8
T002 - Publish the document in Github |  |  |  | 1
T003 - Review the Document |  |  |  | 1
S004 - Create milestone document for the project | 3 | Santhosh | Ongoing
T001- Create milestone document for each sprint |  |  |  | 4
T002 - Publish the document in Github |  |  |  | 1
T003 - Review the Document |  |  |  | 1

## Product Backlog
Task Name | Story | Sprint Ready | Priority | Status | Story Points | Assigned to Sprint
Sprint1 | No | No | High | In progress | 24 | No
S001 - Create Flow Chart | Yes | Yes | High | In progress | 8 | Yes
S002 - Create ERD | Yes | Yes | High | In progress | 8 | Yes
S003 - Create coding standard Document | Yes | Yes | High | In progress | 5 | Yes
S004 - Create milestone document for the project | Yes | Yes | High | Ongoing | 3 | Yes
Sprint2 | No | No | High | In progress | 0 | No

## Test Plan
Project Name |  |  | Version
Test Case ID |  |  | Description
Written By |  |  | Tested on
Tested By
Test # | Date | What to test | Expected Result | Actual result | Status

## User Story
User Story ID | As a | I want to | So that I can

## Project Charter
General Project Information
Project Name | Pass Website
Project Sponsor | Poovanesh
Project Manager
Stakeholders | Poovanesh, Pradeep, Santhosh
Expected Start Date | 2018-03-14
Expected Completion Date
Project Details
Mission | Our mission is to ensure the best relationship with our clients, both during and after their goals have been met. We treat client's website with care. We strive for a modern web layout that is suitable for their needs
Vision | Our vision is to provide entertainment engagement to the clients
Scope | Scope is to develop the website that provide entertainment details to the clients. We will provide movie reviews, list of actvities in and around the city
Success Metrics | Will deploy the project in cloud and make it available for the clients
Date | 2018-03-14